## Introduction
Introduction
Chris: Here are some instructions / helpful tips for using this document. This is a high level document that will encompass all projects. Some of the tabs will be used and broken out seperately for SME's. This document will be streamlined as we move forward and I have a better understanding of our project review phases and timelines. Please scroll down for additional information.

## Master eLearning Project Pl (2
Task ID | Task | Owner(s) | Target Start | Target End | Actual End | Notes | Complete? X
Task ID | Task | Owner(s) | Target Start | Target End | Actual End | Notes | Complete? X
1 | Content Development
1.1 | Kickoff Meeting | Dean/SME
1.2 | Content Due (from SMEs) (Anything beyond How Tos) | SME
1.3 | Initial Content Review | Dean
1.4 | Delivery of Design Document (s) | Dean
1.5 | Approval of Design Document (s) | SME
1.6 | Alpha Delivery of Storyboards (including script/rough images) | Dean
1.7 | Alpha revisions /feedback of Storyboards (including script/images) Content Locked | SME
1.8 | Audio Recording (Audio content locked) | Dean
1.9 | Delivery of Course Assessments | Dean
1.1 | Review Course Assessments | Dean
1.11 | Beta Delivery of Storyboards | SME
1.12 | Beta Feedback of Storyboards (including script/images) | SME
1.13 | Edit materials based on review feedback | Dean
1.14 | Gold Master Delivery: Final Course | Dean
1.15 | Delivery of Published module | Dean
1.16 | Upload and publish to Web/ LMS | Dean
1.17 | Test courses/assessments on Web/LMS | Lori
1.18 | Final courses in Wistia and Select | Lori
1.19 | Content Review of OJT Materials | Lori/SME
1.21 | Delivery of OJT Material (including script/images) | Lori
1.22 | Feedback of OJT Materials | SME
1.22 | Edit materials based on review feedback | Dean
1.23 | Approval of Materials (including script/images) | Dean
1.24 | Post to Training Page/Web | Lori | 2013-07-21
2 | Automatic Drive Time Module
2.1 | Develop Scenes/Graphics for video production | Lori | 2013-04-24 | 2013-04-24
2.2 | Camtasia 101 training | Lori/Ron | 2013-04-25 | 2013-04-25
2.3 | Video Development in Camtasia | Lori | 2013-04-26 | 2013-04-29
2.4 | Post video on Wistia | Lori | 2013-04-30 | 2013-04-30
2.5 | Review of video on Wistia | SME | 2013-04-30 | 2013-05-01
2.6 | Edit video based on review feedback | Lori | 2013-05-02 | 2013-05-02
2.7 | Final Review | SME | 2013-05-03 | 2013-05-03
2.8 | Finalize video and post to TruVu Max Training | Lori | 2013-05-04 | 2013-05-04
2.9 | Email communication to team on Live ADT module | Lori | 2013-05-04
2.1 | Update Video and links on Select | Lori | 2013-05-04
2
2.1
2.2
2.3
2.4
3
3.1
3.2
3.3
3.4
3.5
4
4.1
4.2
4.3
4.4
4.5
5
5.1
5.2
5.3
5.4
5.5

## Project Plan
Task ID | Task | Owner(s) | Target Start | Target End | Actual End | Notes | Complete?
1 | Module 1
1.1 | Kickoff Meeting
1.2
1.3
1.4
1.5
1.6
1.7
1.8
1.9
1.1
1.11
1.12
1.13
1.14
1.15
1.16
1.17
1.18
1.19
1.2
1.21
1.22
1.23
1.24
1.25
1.26
1.27
1.28
1.29
1.3
2 | Module 2
2.1
2.2
2.3
2.4
2.5
2.6
2.7
2.8
2.9
2.1
2.11
2.12
3 | Module 3
3.1
3.2
3.3
3.4
3.5
3.6
3.7
3.8
3.9
3.1
3.11
3.12
3.13
3.14
4 | Module 4
4.1
4.2
4.3
4.4
4.5
4.6
4.7
4.8
4.9
4.1
4.11
4.12
4.13
4.14
4.15
4.16
4.17
4.18
4.19
4.2
4.21
4.22
4.23
4.24
5 | Module 5
5.1
5.2
5.3
5.4
5.5
5.6
5.7
5.8
5.9
5.1
5.11
6 | Module 6
6.1
6.2
6.3
6.4
6.5
6.6
6.7

## Calendar (hidden)
2013
| January | [6 empty] | April | [6 empty] | July | [6 empty] | October | [6 empty] | Milestones and Dates | Number of Days
| S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
|  |  | 2013-01-01 | 2013-01-02 | 2013-01-03 | 2013-01-04 | 2013-01-05 |  | 2013-04-01 | 2013-04-02 | 2013-04-03 | 2013-04-04 | 2013-04-05 | 2013-04-06 |  | 2013-07-01 | 2013-07-02 | 2013-07-03 | 2013-07-04 | 2013-07-05 | 2013-07-06 |  |  | 2013-10-01 | 2013-10-02 | 2013-10-03 | 2013-10-04 | 2013-10-05
| 2013-01-06 | 2013-01-07 | 2013-01-08 | 2013-01-09 | 2013-01-10 | 2013-01-11 | 2013-01-12 | 2013-04-07 | 2013-04-08 | 2013-04-09 | 2013-04-10 | 2013-04-11 | 2013-04-12 | 2013-04-13 | 2013-07-07 | 2013-07-08 | 2013-07-09 | 2013-07-10 | 2013-07-11 | 2013-07-12 | 2013-07-13 | 2013-10-06 | 2013-10-07 | 2013-10-08 | 2013-10-09 | 2013-10-10 | 2013-10-11 | 2013-10-12
| 2013-01-13 | 2013-01-14 | 2013-01-15 | 2013-01-16 | 2013-01-17 | 2013-01-18 | 2013-01-19 | 2013-04-14 | 2013-04-15 | 2013-04-16 | 2013-04-17 | 2013-04-18 | 2013-04-19 | 2013-04-20 | 2013-07-14 | 2013-07-15 | 2013-07-16 | 2013-07-17 | 2013-07-18 | 2013-07-19 | 2013-07-20 | 2013-10-13 | 2013-10-14 | 2013-10-15 | 2013-10-16 | 2013-10-17 | 2013-10-18 | 2013-10-19
| 2013-01-20 | 2013-01-21 | 2013-01-22 | 2013-01-23 | 2013-01-24 | 2013-01-25 | 2013-01-26 | 2013-04-21 | 2013-04-22 | 2013-04-23 | 2013-04-24 | 2013-04-25 | 2013-04-26 | 2013-04-27 | 2013-07-21 | 2013-07-22 | 2013-07-23 | 2013-07-24 | 2013-07-25 | 2013-07-26 | 2013-07-27 | 2013-10-20 | 2013-10-21 | 2013-10-22 | 2013-10-23 | 2013-10-24 | 2013-10-25 | 2013-10-26
| 2013-01-27 | 2013-01-28 | 2013-01-29 | 2013-01-30 | 2013-01-31 |  |  | 2013-04-28 | 2013-04-29 | 2013-04-30 |  |  |  |  | 2013-07-28 | 2013-07-29 | 2013-07-30 | 2013-07-31 |  |  |  | 2013-10-27 | 2013-10-28 | 2013-10-29 | 2013-10-30 | 2013-10-31
| February | [6 empty] | May | [6 empty] | August | [6 empty] | November
| S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
[6 empty] | 2013-02-01 | 2013-02-02 |  |  |  | 2013-05-01 | 2013-05-02 | 2013-05-03 | 2013-05-04 |  |  |  |  | 2013-08-01 | 2013-08-02 | 2013-08-03 | [5 empty] | 2013-11-01 | 2013-11-02
| 2013-02-03 | 2013-02-04 | 2013-02-05 | 2013-02-06 | 2013-02-07 | 2013-02-08 | 2013-02-09 | 2013-05-05 | 2013-05-06 | 2013-05-07 | 2013-05-08 | 2013-05-09 | 2013-05-10 | 2013-05-11 | 2013-08-04 | 2013-08-05 | 2013-08-06 | 2013-08-07 | 2013-08-08 | 2013-08-09 | 2013-08-10 | 2013-11-03 | 2013-11-04 | 2013-11-05 | 2013-11-06 | 2013-11-07 | 2013-11-08 | 2013-11-09
| 2013-02-10 | 2013-02-11 | 2013-02-12 | 2013-02-13 | 2013-02-14 | 2013-02-15 | 2013-02-16 | 2013-05-12 | 2013-05-13 | 2013-05-14 | 2013-05-15 | 2013-05-16 | 2013-05-17 | 2013-05-18 | 2013-08-11 | 2013-08-12 | 2013-08-13 | 2013-08-14 | 2013-08-15 | 2013-08-16 | 2013-08-17 | 2013-11-10 | 2013-11-11 | 2013-11-12 | 2013-11-13 | 2013-11-14 | 2013-11-15 | 2013-11-16
| 2013-02-17 | 2013-02-18 | 2013-02-19 | 2013-02-20 | 2013-02-21 | 2013-02-22 | 2013-02-23 | 2013-05-19 | 2013-05-20 | 2013-05-21 | 2013-05-22 | 2013-05-23 | 2013-05-24 | 2013-05-25 | 2013-08-18 | 2013-08-19 | 2013-08-20 | 2013-08-21 | 2013-08-22 | 2013-08-23 | 2013-08-24 | 2013-11-17 | 2013-11-18 | 2013-11-19 | 2013-11-20 | 2013-11-21 | 2013-11-22 | 2013-11-23
| 2013-02-24 | 2013-02-25 | 2013-02-26 | 2013-02-27 | 2013-02-28 |  |  | 2013-05-26 | 2013-05-27 | 2013-05-28 | 2013-05-29 | 2013-05-30 | 2013-05-31 |  | 2013-08-25 | 2013-08-26 | 2013-08-27 | 2013-08-28 | 2013-08-29 | 2013-08-30 | 2013-08-31 | 2013-11-24 | 2013-11-25 | 2013-11-26 | 2013-11-27 | 2013-11-28 | 2013-11-29 | 2013-11-30
| March | [6 empty] | June | [6 empty] | September | [6 empty] | December
| S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
[6 empty] | 2013-03-01 | 2013-03-02 | [6 empty] | 2013-06-01 | 2013-09-01 | 2013-09-02 | 2013-09-03 | 2013-09-04 | 2013-09-05 | 2013-09-06 | 2013-09-07 | 2013-12-01 | 2013-12-02 | 2013-12-03 | 2013-12-04 | 2013-12-05 | 2013-12-06 | 2013-12-07
| 2013-03-03 | 2013-03-04 | 2013-03-05 | 2013-03-06 | 2013-03-07 | 2013-03-08 | 2013-03-09 | 2013-06-02 | 2013-06-03 | 2013-06-04 | 2013-06-05 | 2013-06-06 | 2013-06-07 | 2013-06-08 | 2013-09-08 | 2013-09-09 | 2013-09-10 | 2013-09-11 | 2013-09-12 | 2013-09-13 | 2013-09-14 | 2013-12-08 | 2013-12-09 | 2013-12-10 | 2013-12-11 | 2013-12-12 | 2013-12-13 | 2013-12-14
| 2013-03-10 | 2013-03-11 | 2013-03-12 | 2013-03-13 | 2013-03-14 | 2013-03-15 | 2013-03-16 | 2013-06-09 | 2013-06-10 | 2013-06-11 | 2013-06-12 | 2013-06-13 | 2013-06-14 | 2013-06-15 | 2013-09-15 | 2013-09-16 | 2013-09-17 | 2013-09-18 | 2013-09-19 | 2013-09-20 | 2013-09-21 | 2013-12-15 | 2013-12-16 | 2013-12-17 | 2013-12-18 | 2013-12-19 | 2013-12-20 | 2013-12-21
| 2013-03-17 | 2013-03-18 | 2013-03-19 | 2013-03-20 | 2013-03-21 | 2013-03-22 | 2013-03-23 | 2013-06-16 | 2013-06-17 | 2013-06-18 | 2013-06-19 | 2013-06-20 | 2013-06-21 | 2013-06-22 | 2013-09-22 | 2013-09-23 | 2013-09-24 | 2013-09-25 | 2013-09-26 | 2013-09-27 | 2013-09-28 | 2013-12-22 | 2013-12-23 | 2013-12-24 | 2013-12-25 | 2013-12-26 | 2013-12-27 | 2013-12-28
| 2013-03-24 | 2013-03-25 | 2013-03-26 | 2013-03-27 | 2013-03-28 | 2013-03-29 | 2013-03-30 | 2013-06-23 | 2013-06-24 | 2013-06-25 | 2013-06-26 | 2013-06-27 | 2013-06-28 | 2013-06-29 | 2013-09-29 | 2013-09-30 | [5 empty] | 2013-12-29 | 2013-12-30 | 2013-12-31
| 2013-03-31 | [6 empty] | 2013-06-30
Blank Calendar- Placeholder

## SME Team Members
ID | Module Name | Project Sponsor (Date) | SME Lead | QA Lead | Additional Resources Y/N
1 | Module 101 | Dean Biele | Dean Biele | Dean Biele
4
7
10
13
16
17
18
19
20

## Decision Log
ID | Description | Decision Team | Decision Deadline (Date) | Decision Reached (Date) | Notes | Decision Reached?
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Question Log
ID | Question | Ask Date | Tasked To | Answer | Answered By | Answer Date | Complete?
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Risk Log
Risk ID |  | Risk | Description | Priority | Assigned to | Mitigation / Action Strategy | Response Date | Status | Close Date | Closed?
1 | L | test | Simulation | Low |  | Meeting with SME to learn |  |  |  | N
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Storyboard Schedule
Task ID | Storyboard Module Name | Owner | Lead SME Delivery Date | Lead SME Review Date | Learning Track | Duration of eLearning (approximate) | Status | Notes
1 | [8 empty] | Status
2 | [8 empty] | Complete
3 | [8 empty] | In Development
4 | [8 empty] | Pending
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## (Module name) Schedule
ID | Module Name | Owner | Lead SME Delivery Date | Lead SME Review Date | Prod LMS Created? | LMS Created? | Status | Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## SAMPLE- module specific
Task ID | Task | Owner(s) | Target Start | Target End | Actual End | Notes | Complete? X
1 | Sample Content Development for eLearning Course (Random dates)
1.1 | Kickoff Meeting | Dean/SME
1.2 | Content Due (from SMEs) (Anything beyond How Tos) | SME
1.3 | Initial Content Review | Dean
1.4 | Delivery of Design Document (s) | Dean
1.5 | Approval of Design Document (s) | SME
1.6 | Alpha Delivery of Storyboards (including script/rough images) | Dean
1.7 | Alpha revisions /feedback of Storyboards (including script/images) Content Locked | SME
1.8 | Audio Recording (Audio content locked) | Dean
1.9 | Delivery of Course Assessments | Dean
1.1 | Review Course Assessments | Dean
1.11 | Beta Delivery of Storyboards | SME
1.12 | Beta Feedback of Storyboards (including script/images) | SME
1.13 | Edit materials based on review feedback | Dean
1.14 | Gold Master Delivery: Final Course | Dean
1.15 | Delivery of Published module | Dean
1.16 | Upload and publish to Web/ LMS | Dean
1.17 | Test courses/assessments on Web/LMS | Dean
1.18 | Final courses in LMS- Live | Dean
2 | OJT Materials
2.1 | Content Review of OJT Materials | Dean/SME
2.2 | Delivery of OJT Material (including script/images) | Dean
2.3 | Feedback of OJT Materials | SME
2.4 | Edit materials based on review feedback | Dean
2.5 | Approval of OJT Materials (including script/images) | Dean
2.6 | Post to Training Page/Web | Dean
3
3.1
3.2
3.3
3.4
3.5
4
4.1
4.2
4.3
4.4
4.5
5
5.1
5.2
5.3
5.4
5.5
6
6.1
6.2
6.3
6.4
6.5

## Edit List
Task ID | Module Name | Course Number (if applicable) | Change Request | Submitted By | Notes / Status | Complete?
1 |  |  |  | Dean
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
Use this sheet ("Edit List") to track change requests once module is complete and has been deployed.
CLICK anywhere on this box to delete these instructions.

## Links
Risk Log - Priority | Storyboard Schedule - Status | Complete - Y/N | Complete - X | User-Names
High | Complete | Y | X | Dean
Alert | In Development | N |  | Biele
Low | Pending