## Introduction (hidden)
Introduction
Chris: Here are some instructions / helpful tips for using this document. This is a high level document that will encompass all projects. Some of the tabs will be used and broken out seperately for SME's. This document will be streamlined as we move forward and I have a better understanding of our project review phases and timelines. Please scroll down for additional information.
Page Layout View
All of the pages are in "Page Layout" view. This makes it easier to change the headers and footers. To change the view back to "normal", choose the "View" tab, then click "Normal" in the Workbook Viewssection. (See screenshot below.)
Deleting and Hiding Worksheets
Where you see a red tab (on the bottom) indicating the name of the worksheet, the red indicates a SAMPLE worksheet with some data pre-populated. You may choose to delete these worksheets by right-mouse-clicking the tab and selecting "Delete". You can also hide the worksheet by right-mouse-clicking the tab and choosing "Hide". Note that if you choose to hide (and ultimately, un-hide) worksheets, there is a worksheed called "Links" which should remain hidden and un-edited. The "Links" worksheet contains the information for all drop-down cells. (See screenshots below.)
Conditional Formatting and Drop-Down Menus
Some worksheets use conditional formatting and drop-down menus. Additionally (as with the "Risk Log") there are locked cells which cannot be filled in by the user (these are automatically populated based on your selections from a drop-down menu). When there is a drop-down menu, conditional formatting may change the color of certain cells (i.e., to gray to indicate the task-item is complete, or to red, yellow, or green indicating the level of a risk). (See example screenshots below.)
Grouping and Ungrouping Rows
Groups are filters which allow you to roll up (condense) items in the same group.
Instruction Boxes
If you see any instructions on a sheet in a blue box, you can delete the instructions by clicking anywhere on the blue box.
Calendar
There is a calendar (and a sample calendar) which will help determine target dates and milestones. To add a comment into a date field, double-click the cell and enter the comment. The year is set for 2013, but if you need to change the date, use the spinner control next to the year.

## Project Plan
Task ID | Task | Owner(s) | Target Start | Target End | Actual End | Notes | Complete?
1 | Module 1
1.1 | Kickoff Meeting | [5 empty] | X
1.2 | Content Due (from SMEs) (Access to SW- Installed) | [5 empty] | X
1.3 | Initial Content Review / Storyboard/ Programming | [5 empty] | X
1.4 | Prototype Delivery (eLearning Format) | [5 empty] | X
1.5 | Alpha Delivery of Storyboards (including script/rough images) | [5 empty] | X
1.6 | Alpha revisions /feedback of Storyboards (including script/images) Content Locked
1.6b | Kickoff: Modifying a Scope
1.6C | Design Document: Part 2
1.CC | Feedback on Design Document
1.6D | Writing and Development
1.7 | Storyboard Approval
1.6 | Audio Recording (Audio content locked)
1.7 | Beta Delivery of Course
1.8 | Beta Feedback of Course
1.9 | Edit materials based on review feedback
1.1 | Gold Master Delivery: Final Course
1.15 | Load and Post to Wistia
1.16 | Email to Learning Team
1.17 | Post to TruVu Select
1.18
1.29
1.3
2 | Module2
2.1 | Kickoff Meeting
2.2 | Content Due (from SMEs) (Access to SW- Installed)
2.3 | Initial Content Review / Storyboard/ Programming
2.4 | Prototype Delivery (eLearning Format)
2.5 | Alpha Delivery of Storyboards (including script/rough images)
2.6 | Alpha revisions /feedback of Storyboards (including script/images) Content Locked
2.7 | Audio Recording (Audio content locked)
2.8 | Beta Delivery of Course
2.9 | Beta Feedback of Course
2.1 | Edit materials based on review feedback
2.11 | Gold Master Delivery: Final Course
2.12
3 | Module 3
3.1 | Kickoff Meeting
3.2 | Content Due (from SMEs) (Access to SW- Installed)
3.3 | Design Document
3.4 | Initial Content Review / Storyboard/ Programming
3.5 | Alpha Delivery of Storyboards (including script/rough images)
3.6 | Alpha revisions /feedback of Storyboards (including script/images) Content Locked
3.7 | Audio Recording (Audio content locked)
3.8 | Beta Delivery of Course
3.9 | Beta Feedback of Course
3.1 | Edit materials based on review feedback
3.11 | Gold Master Delivery: Final Course
3.12 | Load and Post to Wistia
3.13
3.14
4 | Module 4
4.1 | Kickoff Meeting
4.2 | Content Due (from SMEs) (Access to SW- Installed)
4.3 | Design Document
4.3a | Design Document Review
4.4 | Initial Content Review / Storyboard/ Programming
4.5 | Alpha Delivery of Storyboards (including script/rough images)
4.6 | Alpha revisions /feedback of Storyboards (including script/images) Content Locked
4.7 | Audio Recording (Audio content locked)
4.8 | Beta Delivery of Course
4.9 | Beta Feedback of Course
4.1 | Edit materials based on review feedback
4.11 | Gold Master Delivery: Final Course
4.12 | Load and Post to Wistia
4.13
4.14
4.15
4.16
4.17
4.18
4.19
4.2
4.21
4.22
4.23
4.24
5 | Module 5
5.1 | Kickoff Meeting | [5 empty] | X
5.2 | Content Due (from SMEs) (Access to SW- Installed)
0.20833 | Design Document
5.3 | Initial Content Review / Storyboard/ Programming
5.4 | Alpha Delivery of Storyboards (including script/rough images)
5.5 | Alpha revisions /feedback of Storyboards (including script/images) Content Locked
5.6 | Audio Recording (Audio content locked)
5.7 | Beta Delivery of Course | Lori
5.8 | Beta Feedback of Course | Kristin
5.9 | Edit materials based on review feedback | Lori
5.1 | Gold Master Delivery: Final Course | Lori
5.11 | Load and Post to Wistia | Lori
6 | Module 6
6.1 | On Hold
6.2
6.3
6.4
6.5
6.6
6.7
7 | Introduction to 4.0 Overview
7 | Module 7
8 | Module 8

## SME Team Members
ID | Module Name | Project Sponsor | SME Lead | QA Lead | Completed?
1 | Module 101 | Dean Biele | Biele Dean | Dean Biele
After 1.0 release

## Decision Log
ID | Description | Decision Team | Decision Deadline (Date) | Decision Reached (Date) | Notes | Decision Reached?
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Question Log (hidden)
ID | Question | Ask Date | Tasked To | Answer | Answered By | Answer Date | Complete?
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Risk Log
Risk ID |  | Risk | Description | Priority | Assigned to | Mitigation / Action Strategy | Response Date | Status | Close Date | Closed?
1 | A |  |  | Alert | [5 empty] | N
2 | A |  |  | Alert | [5 empty] | N
3 | H |  |  | High | [5 empty] | Y
4 | H |  |  | High | [5 empty] | y
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Storyboard Schedule (hidden)
Task ID | Storyboard Module Name | Owner | Lead SME Delivery Date | Lead SME Review Date | Learning Track | Duration of eLearning (approximate) | Status | Notes
1 | [8 empty] | Status
2 | [8 empty] | Complete
3 | [8 empty] | In Development
4 | [8 empty] | Pending
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## OJT Schedule
ID | OJT Module Name | Owner | Lead SME Delivery Date | Lead SME Review Date | P Created? | L Created? | Status | Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Link
Names
Dean Biele
Biele Dean

## SAMPLE-Calendar (hidden)
2013
| January | [6 empty] | April | [6 empty] | July | [6 empty] | October | [6 empty] | Milestones and Dates | Number of Days
| S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
|  |  | 2013-01-01 | 2013-01-02 | 2013-01-03 | 2013-01-04 | 2013-01-05 |  | 2013-04-01 | 2013-04-02 | 2013-04-03 | 2013-04-04 | 2013-04-05 | 2013-04-06 |  | 2013-07-01 | 2013-07-02 | 2013-07-03 | 2013-07-04 | 2013-07-05 | 2013-07-06 |  |  | 2013-10-01 | 2013-10-02 | 2013-10-03 | 2013-10-04 | 2013-10-05 | Kickoff (CV): 4/23-24 | 2
| 2013-01-06 | 2013-01-07 | 2013-01-08 | 2013-01-09 | 2013-01-10 | 2013-01-11 | 2013-01-12 | 2013-04-07 | 2013-04-08 | 2013-04-09 | 2013-04-10 | 2013-04-11 | 2013-04-12 | 2013-04-13 | 2013-07-07 | 2013-07-08 | 2013-07-09 | 2013-07-10 | 2013-07-11 | 2013-07-12 | 2013-07-13 | 2013-10-06 | 2013-10-07 | 2013-10-08 | 2013-10-09 | 2013-10-10 | 2013-10-11 | 2013-10-12
| 2013-01-13 | 2013-01-14 | 2013-01-15 | 2013-01-16 | 2013-01-17 | 2013-01-18 | 2013-01-19 | 2013-04-14 | 2013-04-15 | 2013-04-16 | 2013-04-17 | 2013-04-18 | 2013-04-19 | 2013-04-20 | 2013-07-14 | 2013-07-15 | 2013-07-16 | 2013-07-17 | 2013-07-18 | 2013-07-19 | 2013-07-20 | 2013-10-13 | 2013-10-14 | 2013-10-15 | 2013-10-16 | 2013-10-17 | 2013-10-18 | 2013-10-19
| 2013-01-20 | 2013-01-21 | 2013-01-22 | 2013-01-23 | 2013-01-24 | 2013-01-25 | 2013-01-26 | 2013-04-21 | 2013-04-22 | 2013-04-23 | 2013-04-24 | 2013-04-25 | 2013-04-26 | 2013-04-27 | 2013-07-21 | 2013-07-22 | 2013-07-23 | 2013-07-24 | 2013-07-25 | 2013-07-26 | 2013-07-27 | 2013-10-20 | 2013-10-21 | 2013-10-22 | 2013-10-23 | 2013-10-24 | 2013-10-25 | 2013-10-26
| 2013-01-27 | 2013-01-28 | 2013-01-29 | 2013-01-30 | 2013-01-31 |  |  | 2013-04-28 | 2013-04-29 | 2013-04-30 |  |  |  |  | 2013-07-28 | 2013-07-29 | 2013-07-30 | 2013-07-31 |  |  |  | 2013-10-27 | 2013-10-28 | 2013-10-29 | 2013-10-30 | 2013-10-31
| February | [6 empty] | May | [6 empty] | August | [6 empty] | November
| S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
[6 empty] | 2013-02-01 | 2013-02-02 |  |  |  | 2013-05-01 | 2013-05-02 | 2013-05-03 | 2013-05-04 |  |  |  |  | 2013-08-01 | 2013-08-02 | 2013-08-03 | [5 empty] | 2013-11-01 | 2013-11-02
| 2013-02-03 | 2013-02-04 | 2013-02-05 | 2013-02-06 | 2013-02-07 | 2013-02-08 | 2013-02-09 | 2013-05-05 | 2013-05-06 | 2013-05-07 | 2013-05-08 | 2013-05-09 | 2013-05-10 | 2013-05-11 | 2013-08-04 | 2013-08-05 | 2013-08-06 | 2013-08-07 | 2013-08-08 | 2013-08-09 | 2013-08-10 | 2013-11-03 | 2013-11-04 | 2013-11-05 | 2013-11-06 | 2013-11-07 | 2013-11-08 | 2013-11-09
| 2013-02-10 | 2013-02-11 | 2013-02-12 | 2013-02-13 | 2013-02-14 | 2013-02-15 | 2013-02-16 | 2013-05-12 | 2013-05-13 | 2013-05-14 | 2013-05-15 | 2013-05-16 | 2013-05-17 | 2013-05-18 | 2013-08-11 | 2013-08-12 | 2013-08-13 | 2013-08-14 | 2013-08-15 | 2013-08-16 | 2013-08-17 | 2013-11-10 | 2013-11-11 | 2013-11-12 | 2013-11-13 | 2013-11-14 | 2013-11-15 | 2013-11-16
| 2013-02-17 | 2013-02-18 | 2013-02-19 | 2013-02-20 | 2013-02-21 | 2013-02-22 | 2013-02-23 | 2013-05-19 | 2013-05-20 | 2013-05-21 | 2013-05-22 | 2013-05-23 | 2013-05-24 | 2013-05-25 | 2013-08-18 | 2013-08-19 | 2013-08-20 | 2013-08-21 | 2013-08-22 | 2013-08-23 | 2013-08-24 | 2013-11-17 | 2013-11-18 | 2013-11-19 | 2013-11-20 | 2013-11-21 | 2013-11-22 | 2013-11-23
| 2013-02-24 | 2013-02-25 | 2013-02-26 | 2013-02-27 | 2013-02-28 |  |  | 2013-05-26 | 2013-05-27 | 2013-05-28 | 2013-05-29 | 2013-05-30 | 2013-05-31 |  | 2013-08-25 | 2013-08-26 | 2013-08-27 | 2013-08-28 | 2013-08-29 | 2013-08-30 | 2013-08-31 | 2013-11-24 | 2013-11-25 | 2013-11-26 | 2013-11-27 | 2013-11-28 | 2013-11-29 | 2013-11-30
[29 empty] | Design Documents: 10/1 - 10/31 | 23
| March | [6 empty] | June | [6 empty] | September | [6 empty] | December | [6 empty] | WSI review meeting: 11/1 - 11/8 | 6
| S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | Final edits of Weather Module 1: 11/11 - 11/29 | 15
[6 empty] | 2013-03-01 | 2013-03-02 | [6 empty] | 2013-06-01 | 2013-09-01 | 2013-09-02 | 2013-09-03 | 2013-09-04 | 2013-09-05 | 2013-09-06 | 2013-09-07 | 2013-12-01 | 2013-12-02 | 2013-12-03 | 2013-12-04 | 2013-12-05 | 2013-12-06 | 2013-12-07 | Launch of Revision X.X: 12/3
| 2013-03-03 | 2013-03-04 | 2013-03-05 | 2013-03-06 | 2013-03-07 | 2013-03-08 | 2013-03-09 | 2013-06-02 | 2013-06-03 | 2013-06-04 | 2013-06-05 | 2013-06-06 | 2013-06-07 | 2013-06-08 | 2013-09-08 | 2013-09-09 | 2013-09-10 | 2013-09-11 | 2013-09-12 | 2013-09-13 | 2013-09-14 | 2013-12-08 | 2013-12-09 | 2013-12-10 | 2013-12-11 | 2013-12-12 | 2013-12-13 | 2013-12-14 | Pilot: 12/9
| 2013-03-10 | 2013-03-11 | 2013-03-12 | 2013-03-13 | 2013-03-14 | 2013-03-15 | 2013-03-16 | 2013-06-09 | 2013-06-10 | 2013-06-11 | 2013-06-12 | 2013-06-13 | 2013-06-14 | 2013-06-15 | 2013-09-15 | 2013-09-16 | 2013-09-17 | 2013-09-18 | 2013-09-19 | 2013-09-20 | 2013-09-21 | 2013-12-15 | 2013-12-16 | 2013-12-17 | 2013-12-18 | 2013-12-19 | 2013-12-20 | 2013-12-21
| 2013-03-17 | 2013-03-18 | 2013-03-19 | 2013-03-20 | 2013-03-21 | 2013-03-22 | 2013-03-23 | 2013-06-16 | 2013-06-17 | 2013-06-18 | 2013-06-19 | 2013-06-20 | 2013-06-21 | 2013-06-22 | 2013-09-22 | 2013-09-23 | 2013-09-24 | 2013-09-25 | 2013-09-26 | 2013-09-27 | 2013-09-28 | 2013-12-22 | 2013-12-23 | 2013-12-24 | 2013-12-25 | 2013-12-26 | 2013-12-27 | 2013-12-28
| 2013-03-24 | 2013-03-25 | 2013-03-26 | 2013-03-27 | 2013-03-28 | 2013-03-29 | 2013-03-30 | 2013-06-23 | 2013-06-24 | 2013-06-25 | 2013-06-26 | 2013-06-27 | 2013-06-28 | 2013-06-29 | 2013-09-29 | 2013-09-30 | [5 empty] | 2013-12-29 | 2013-12-30 | 2013-12-31
| 2013-03-31 | [6 empty] | 2013-06-30
SAMPLE
Sample Calendar that we can decide to use for at-a-glance scheduling.
.
Note on W4: July 4th Holiday - US
Note on AC4: Work on FG/PG/Handouts
Note on AF13: Review of wsi review meeting
Note on AB15: Final edits of weather module
Note on AA16: Biele, Lori: Lori's Birthday
Note on AE16: Thanksgiving Holiday - US
Note on L17: Memorial Day Holiday - US
Note on T22: Labor Day - US
Note on AC22: All documents to Mimeo for printing
Note on L24: Team Site Meeting
Note on AD25: Christmas

## Calendar (hidden)
2013
| January | [6 empty] | April | [6 empty] | July | [6 empty] | October | [6 empty] | Milestones and Dates | Number of Days
| S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
|  |  | 2013-01-01 | 2013-01-02 | 2013-01-03 | 2013-01-04 | 2013-01-05 |  | 2013-04-01 | 2013-04-02 | 2013-04-03 | 2013-04-04 | 2013-04-05 | 2013-04-06 |  | 2013-07-01 | 2013-07-02 | 2013-07-03 | 2013-07-04 | 2013-07-05 | 2013-07-06 |  |  | 2013-10-01 | 2013-10-02 | 2013-10-03 | 2013-10-04 | 2013-10-05
| 2013-01-06 | 2013-01-07 | 2013-01-08 | 2013-01-09 | 2013-01-10 | 2013-01-11 | 2013-01-12 | 2013-04-07 | 2013-04-08 | 2013-04-09 | 2013-04-10 | 2013-04-11 | 2013-04-12 | 2013-04-13 | 2013-07-07 | 2013-07-08 | 2013-07-09 | 2013-07-10 | 2013-07-11 | 2013-07-12 | 2013-07-13 | 2013-10-06 | 2013-10-07 | 2013-10-08 | 2013-10-09 | 2013-10-10 | 2013-10-11 | 2013-10-12
| 2013-01-13 | 2013-01-14 | 2013-01-15 | 2013-01-16 | 2013-01-17 | 2013-01-18 | 2013-01-19 | 2013-04-14 | 2013-04-15 | 2013-04-16 | 2013-04-17 | 2013-04-18 | 2013-04-19 | 2013-04-20 | 2013-07-14 | 2013-07-15 | 2013-07-16 | 2013-07-17 | 2013-07-18 | 2013-07-19 | 2013-07-20 | 2013-10-13 | 2013-10-14 | 2013-10-15 | 2013-10-16 | 2013-10-17 | 2013-10-18 | 2013-10-19
| 2013-01-20 | 2013-01-21 | 2013-01-22 | 2013-01-23 | 2013-01-24 | 2013-01-25 | 2013-01-26 | 2013-04-21 | 2013-04-22 | 2013-04-23 | 2013-04-24 | 2013-04-25 | 2013-04-26 | 2013-04-27 | 2013-07-21 | 2013-07-22 | 2013-07-23 | 2013-07-24 | 2013-07-25 | 2013-07-26 | 2013-07-27 | 2013-10-20 | 2013-10-21 | 2013-10-22 | 2013-10-23 | 2013-10-24 | 2013-10-25 | 2013-10-26
| 2013-01-27 | 2013-01-28 | 2013-01-29 | 2013-01-30 | 2013-01-31 |  |  | 2013-04-28 | 2013-04-29 | 2013-04-30 |  |  |  |  | 2013-07-28 | 2013-07-29 | 2013-07-30 | 2013-07-31 |  |  |  | 2013-10-27 | 2013-10-28 | 2013-10-29 | 2013-10-30 | 2013-10-31
| February | [6 empty] | May | [6 empty] | August | [6 empty] | November
| S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
[6 empty] | 2013-02-01 | 2013-02-02 |  |  |  | 2013-05-01 | 2013-05-02 | 2013-05-03 | 2013-05-04 |  |  |  |  | 2013-08-01 | 2013-08-02 | 2013-08-03 | [5 empty] | 2013-11-01 | 2013-11-02
| 2013-02-03 | 2013-02-04 | 2013-02-05 | 2013-02-06 | 2013-02-07 | 2013-02-08 | 2013-02-09 | 2013-05-05 | 2013-05-06 | 2013-05-07 | 2013-05-08 | 2013-05-09 | 2013-05-10 | 2013-05-11 | 2013-08-04 | 2013-08-05 | 2013-08-06 | 2013-08-07 | 2013-08-08 | 2013-08-09 | 2013-08-10 | 2013-11-03 | 2013-11-04 | 2013-11-05 | 2013-11-06 | 2013-11-07 | 2013-11-08 | 2013-11-09
| 2013-02-10 | 2013-02-11 | 2013-02-12 | 2013-02-13 | 2013-02-14 | 2013-02-15 | 2013-02-16 | 2013-05-12 | 2013-05-13 | 2013-05-14 | 2013-05-15 | 2013-05-16 | 2013-05-17 | 2013-05-18 | 2013-08-11 | 2013-08-12 | 2013-08-13 | 2013-08-14 | 2013-08-15 | 2013-08-16 | 2013-08-17 | 2013-11-10 | 2013-11-11 | 2013-11-12 | 2013-11-13 | 2013-11-14 | 2013-11-15 | 2013-11-16
| 2013-02-17 | 2013-02-18 | 2013-02-19 | 2013-02-20 | 2013-02-21 | 2013-02-22 | 2013-02-23 | 2013-05-19 | 2013-05-20 | 2013-05-21 | 2013-05-22 | 2013-05-23 | 2013-05-24 | 2013-05-25 | 2013-08-18 | 2013-08-19 | 2013-08-20 | 2013-08-21 | 2013-08-22 | 2013-08-23 | 2013-08-24 | 2013-11-17 | 2013-11-18 | 2013-11-19 | 2013-11-20 | 2013-11-21 | 2013-11-22 | 2013-11-23
| 2013-02-24 | 2013-02-25 | 2013-02-26 | 2013-02-27 | 2013-02-28 |  |  | 2013-05-26 | 2013-05-27 | 2013-05-28 | 2013-05-29 | 2013-05-30 | 2013-05-31 |  | 2013-08-25 | 2013-08-26 | 2013-08-27 | 2013-08-28 | 2013-08-29 | 2013-08-30 | 2013-08-31 | 2013-11-24 | 2013-11-25 | 2013-11-26 | 2013-11-27 | 2013-11-28 | 2013-11-29 | 2013-11-30
| March | [6 empty] | June | [6 empty] | September | [6 empty] | December
| S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
[6 empty] | 2013-03-01 | 2013-03-02 | [6 empty] | 2013-06-01 | 2013-09-01 | 2013-09-02 | 2013-09-03 | 2013-09-04 | 2013-09-05 | 2013-09-06 | 2013-09-07 | 2013-12-01 | 2013-12-02 | 2013-12-03 | 2013-12-04 | 2013-12-05 | 2013-12-06 | 2013-12-07
| 2013-03-03 | 2013-03-04 | 2013-03-05 | 2013-03-06 | 2013-03-07 | 2013-03-08 | 2013-03-09 | 2013-06-02 | 2013-06-03 | 2013-06-04 | 2013-06-05 | 2013-06-06 | 2013-06-07 | 2013-06-08 | 2013-09-08 | 2013-09-09 | 2013-09-10 | 2013-09-11 | 2013-09-12 | 2013-09-13 | 2013-09-14 | 2013-12-08 | 2013-12-09 | 2013-12-10 | 2013-12-11 | 2013-12-12 | 2013-12-13 | 2013-12-14
| 2013-03-10 | 2013-03-11 | 2013-03-12 | 2013-03-13 | 2013-03-14 | 2013-03-15 | 2013-03-16 | 2013-06-09 | 2013-06-10 | 2013-06-11 | 2013-06-12 | 2013-06-13 | 2013-06-14 | 2013-06-15 | 2013-09-15 | 2013-09-16 | 2013-09-17 | 2013-09-18 | 2013-09-19 | 2013-09-20 | 2013-09-21 | 2013-12-15 | 2013-12-16 | 2013-12-17 | 2013-12-18 | 2013-12-19 | 2013-12-20 | 2013-12-21
| 2013-03-17 | 2013-03-18 | 2013-03-19 | 2013-03-20 | 2013-03-21 | 2013-03-22 | 2013-03-23 | 2013-06-16 | 2013-06-17 | 2013-06-18 | 2013-06-19 | 2013-06-20 | 2013-06-21 | 2013-06-22 | 2013-09-22 | 2013-09-23 | 2013-09-24 | 2013-09-25 | 2013-09-26 | 2013-09-27 | 2013-09-28 | 2013-12-22 | 2013-12-23 | 2013-12-24 | 2013-12-25 | 2013-12-26 | 2013-12-27 | 2013-12-28
| 2013-03-24 | 2013-03-25 | 2013-03-26 | 2013-03-27 | 2013-03-28 | 2013-03-29 | 2013-03-30 | 2013-06-23 | 2013-06-24 | 2013-06-25 | 2013-06-26 | 2013-06-27 | 2013-06-28 | 2013-06-29 | 2013-09-29 | 2013-09-30 | [5 empty] | 2013-12-29 | 2013-12-30 | 2013-12-31
| 2013-03-31 | [6 empty] | 2013-06-30
Blank Calendar- Placeholder

## SAMPLE- module specific (hidden)
Task ID | Task | Owner(s) | Target Start | Target End | Actual End | Notes | Complete? X
1 | Sample Content Development for eLearning Course (Random dates)
1.1 | Kickoff Meeting | Lori/SME | 2013-04-15
1.2 | Content Due (from SMEs) (Anything beyond How Tos) | SME | 2013-04-15
1.3 | Initial Content Review | Lori | 2013-04-16
1.4 | Delivery of Design Document (s) | Lori | 2013-04-20
1.5 | Approval of Design Document (s) | SME | 2013-04-13
1.6 | Alpha Delivery of Storyboards (including script/rough images) | Lori | 2013-05-08
1.7 | Alpha revisions /feedback of Storyboards (including script/images) Content Locked | SME | 2013-05-15
1.8 | Audio Recording (Audio content locked) | Lori | 2013-05-22
1.9 | Delivery of Course Assessments | Lori | 2013-05-22
1.1 | Review Course Assessments | Don | 2013-05-24
1.11 | Beta Delivery of Storyboards | SME | 2013-06-05
1.12 | Beta Feedback of Storyboards (including script/images) | SME | 2013-06-12
1.13 | Edit materials based on review feedback | Lori | 2013-06-13
1.14 | Gold Master Delivery: Final Course | Lori | 2013-06-21
1.15 | Delivery of Published module | Lori | 2013-06-26
1.16 | Upload and publish to Web/ LMS | Lori | 2013-06-28
1.17 | Test courses/assessments on Web/LMS | Lori | 2013-07-01
1.18 | Final courses in LMS- Live | Lori | 2013-07-05
2 | OJT Materials
2.1 | Content Review of OJT Materials | Lori/SME | 2013-04-15
2.2 | Delivery of OJT Material (including script/images) | Lori | 2013-07-05
2.3 | Feedback of OJT Materials | SME | 2013-07-11
2.4 | Edit materials based on review feedback | Lori | 2013-07-14
2.5 | Approval of OJT Materials (including script/images) | Lori | 2013-07-17
2.6 | Post to Training Page/Web | Lori | 2013-07-21
3
3.1
3.2
3.3
3.4
3.5
4
4.1
4.2
4.3
4.4
4.5
5
5.1
5.2
5.3
5.4
5.5
6
6.1
6.2
6.3
6.4
6.5

## Edit List (hidden)
Task ID | Module Name | Course Number (if applicable) | Change Request | Submitted By | Notes / Status | Complete?
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
Use this sheet ("Edit List") to track change requests once module is complete and has been deployed.
CLICK anywhere on this box to delete these instructions.

## Links (hidden)
Risk Log - Priority | Storyboard Schedule - Status | Complete - Y/N | Complete - X
High | Complete | Y | X
Alert | In Development | N
Low | Pending